## Comps
|  |  | ONE BEDROOM | [8 empty] | TWO BEDROOMS | [6 empty] | THREE BEDROOMS
|  |  | SMALLER |  |  |  | LARGER |  |  |  | ONE BATH |  |  |  | TWO BATH |  |  |  | TWO BATH |  |  |  | THREE & THREE 1/2 BATH |  |  |  | FOUR BEDROOMS |  |  |  | THREE BATH |  |  |  | FOUR BATH
| Total Units | Age | Size | Rent | Rent/SF | Rent/Bdrm | Size | Rent | Rent/SF | Rent/Bdrm | Size | Rent | Rent/SF | Rent/Bdrm | Size | Rent | Rent/SF | Rent/Bdrm | Size | Rent | Rent/SF | Rent/Bdrm | Size | Rent | Rent/SF | Rent/Bdrm | Size | Rent | Rent/SF | Rent/Bdrm | Size | Rent | Rent/SF | Rent/Bdrm | Size | Rent | Rent/SF | Rent/Bdrm
Jefferson | 173 | 1 | 477 | 650 | 1.36 | 650 | [8 empty] | 800 | 1000 | 1.25 | 500 |  |  |  |  | 944 | 1374 | 1.46 | 458 | 1100 | 1600 | 1.45 | 400
The Palazzo | 152 | 3 | 689 | 705 | 1.02 | 705 | 806 | 755 | 0.94 | 755 | 988 | 910 | 0.92 | 455 | 1105 | 1025 | 0.93 | 512.5 | 1250 | 1210 | 0.97 | 403.33 | 1250 | 1210 | 0.97 | 403.33 | 1350 | 1624 | 1.2 | 406
Hillside Ranch | 258 | 3 | 501 | 600 | 1.2 | 600 | 755 | 725 | 0.96 | 725 | 886 | 810 | 0.91 | 405 | 933 | 900 | 0.96 | 450 | [8 empty] | 1556 | 1880 | 1.21 | 470
Sterling Univ. Apts. | 192 | 3 | [12 empty] | 1058 | 1064 | 1.01 | 532 |  |  |  |  | 1000 | 1281 | 1.28 | 427
Sterling Univ. Apts. | [14 empty] | 1058 | 976 | 0.92 | 488
[15 empty] | 990.8 | 993 | 1.01 | 496.5 | 1250 | 1210 | 0.97 | 403.33 | 1064.6667 | 1288.3333 | 1.2367 | 429.4433 | 1335.3333 | 1701.3333 | 1.2867 | 425.3333
SM134 | 134 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 1107 | 1150 | 1.0388 | 575 |  |  |  |  | 1298 | 1425 | 1.0978 | 475
[15 empty] | 1198 | 1200 | 1.0017 | 600
[15 empty] | 957 | 1200 | 1 | 600
[15 empty] | 1198 | 1497.5 | 1.25 | 748.75
Note on U12: Suggested Repair:W12*2.0
Note on U13: Suggested Repair:W13*2.0
Note on V14: Suggested Repair:U14/T14 Suggested Value:1.2539184952978057
Note on W14: Suggested Repair:U14/2.0
Note on V15: Suggested Repair:U15/T15

## Project Schedule
| Man Days | 2000-12-18 | 2000-12-25 | 36892 | 36899 | 36906 | 36913 | 36920 | 36927 | 36934 | 36941 | 36948 | 36955 | 36962 | 36969 | 36976 | 36983 | 36990 | 36997 | 37004 | 37011 | 37018 | 37025 | 37032 | 37039 | 37046 | 37053 | 37060 | 37067 | 37074 | 37081 | 37088 | 37095 | 37102 | 37109 | 37116 | 37123 | 37130 | 37137 | 37144 | 37151 | 37158 | 37165 | 37172 | 37179 | 37186 | 37193 | 37200 | 37207 | 37214 | 37221 | 37228 | 37235 | 37242 | 37249 | 37256 | 37263 | 37270 | 37277 | 37284 | 37291 | 37298 | 37305 | 37312 | 37319 | 37326 | 37333 | 37340 | 37347 | 37354 | 37361 | 37368 | 37375 | 37382 | 37389 | 37396 | 37403 | 37410 | 37417 | 37424 | 37431 | 37438 | 37445 | 37452 | 37459 | 37466 | 37473 | 37480 | 37487 | 37494 | 37501 | 37508 | 37515 | 37522 | 37529 | 37536 | 37543 | 37550
Number of Months | [5 empty] | 0 | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4 | 4.25 | 4.5 | 4.75 | 5 | 5.25 | 5.5 | 5.75 | 6 | 6.25 | 6.5 | 6.75 | 7 | 7.25 | 7.5 | 7.75 | 8 | 8.25 | 8.5 | 8.75 | 9 | 9.25 | 9.5 | 9.75 | 10 | 10.25 | 10.5 | 10.75 | 11 | 11.25 | 11.5 | 11.75 | 12 | 12.25 | 12.5 | 12.75 | 13 | 13.25 | 13.5 | 13.75 | 14 | 14.25 | 14.5 | 14.75 | 15 | 15.25 | 15.5 | 15.75 | 16 | 16.25 | 16.5 | 16.75 | 17 | 17.25 | 17.5 | 17.75 | 18 | 18.25 | 18.5 | 18.75 | 19 | 19.25 | 19.5 | 19.75 | 20 | 20.25 | 20.5 | 20.75 | 21
1 YEAR
Second Contract Extension |  | x
Loan Package Final |  | x
Appraisal Complete |  | x
Closing Loan/Land |  |  |  |  | x
Survey & Topo | 10 |  | x | x | x |  | x | x | x
Partnership Agreement
Re-Plat 2nd Parcel-Eng | 2 |  |  |  | x |  | x
Re-Plat 2nd Parcel-Approval | 22 | [6 empty] | x | x | x | x
Utility Design | [9 empty] | x | x |  | x | x
Architectural Plans
PK Review of Plans
Creekside Review of Plans
City Submission | [13 empty] | x | x | x | x | x
City Approval
Supervisor Start
Bidding-Site Improvements
Bid Review
Bidding-Unit Construction
Bid Review
Improvements
Excavation/Embankment | [17 empty] | x
8" Flex Base
8"PVC Watermain
2" PVC Watermain
8" Wastewater Line(all depths)
W.W. Manholes
Water Services
Master Meters
Fire Hydrants W/Valve
Wet Tap 8"
Electrical
HighSpeed T-1 Line
1 1/2" HMAC
Curb & Gutter
Striping
Ammenities
Perimeter Wall
Swimming Pool
Basketball Court
Volleyball Court
Rental Offices
Fitness Center
Technology Center
Landscaping & Sprinklers
Entry Gates
Unit Construction - 33 Bldgs
Phase 1 - 4 Bldgs + Mgr Office | 132 | Man Days | [18 empty] | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4
Phase 2 - 4 Bldgs | 110 | Man Days | [22 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Phase 3 - 4 Bldgs | 110 | Man Days | [25 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Phase 4 - 4 Bldgs | 110 | Man Days | [28 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Phase 5 - 4 Bldgs | 110 | Man Days | [31 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Phase 6 - 4 Bldgs | 110 | Man Days | [34 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Phase 7 - 4 Bldgs | 110 | Man Days | [37 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Phase 8 - 4 Bldgs | 110 | Man Days | [40 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Pre-Leasing
Phase 1 | 17 | Units | [25 empty] | 17
Phase 2 | 17 | Units | [25 empty] | 17
Phase 3 | 17 | Units | [29 empty] | 17
Phase 4 | 17 | Units | [29 empty] | 17
Phase 5 | 17 | Units | [29 empty] | 17
Phase 6 | 16 | Units | [29 empty] | 17
Phase 7 | 16 | Units | [29 empty] | 17
Phase 8 | 16 | Units | [29 empty] | 17
| 133 | Units
Rent Stabilization
Appraisal for Permanent
Close On Permanent
Note on E1: Suggested Repair:D1+7.0